# RESOURCE ALLOCATION

1.1. Leadership Approach and Resource Alignment

- Emphasis on servant leadership instead of command-and-control

- Ensures psychological safety for better team performance

- Aligns resources with project goals and deliverables

- Supports efficient utilization within 3.5-week timeline

- Promotes accountability and ownership of tasks

1.2. Resource Identification

- Human (5 members across SPM & SRE sub-teams)

- Physical (personal laptops, dev workstations)

- Financial (free-tier cloud services)

- Informational (project docs, AI APIs, open-source libraries)

1.3. RACI Matrix

| Activity | SPM1 | SPM2 | SPM3 | SRE1 | SRE2 |
| --- | --- | --- | --- | --- | --- |
| Planning | A | C | C | I | I |
| Requirements | A | R | C | I | I |
| Design | A | C | R | I | C |
| Development | A | R | R | I | C |
| AI Module | A | I | C | C | R |
| Testing | A | I | C | R | I |
| Deployment | A | R | R | C | I |

1.4. Resource Allocation & Cost

| Resource | Rate | Hours | Cost |
| --- | --- | --- | --- |
| SPM1 | 800 | 60 | 48000 |
| SPM2 | 700 | 85 | 59500 |
| SPM3 | 800 | 95 | 76000 |
| SRE1 | 600 | 50 | 30000 |
| SRE2 | 900 | 70 | 63000 |

Total Direct Cost = PKR 276,500

1.5. Resource Allocation Strategy

- Parallel development (frontend & backend)

- Modular AI development

- Skill-based task assignment

- Early testing integration

1.6. Resource Leveling Strategies

- Task Prioritization

  - Critical tasks (backend + AI integration) completed first

- Workload Smoothing

  - Prevents overload of SPM3 and SRE2 during peak development

- Task Reallocation

  - Frontend tasks redistributed to balance workload

- Time Shifting

  - Non-critical tasks moved to later sprint phases

- Parallel Execution Control

  - Ensures frontend, backend, and AI modules progress simultaneously without bottlenecks

1.7. Resource Monitoring and Control

- Weekly progress tracking

- Task monitoring

- Issue tracking

Corrective actions:

- Task reassignment

- Workload redistribution

- Increased effort when required

1.8. Resource Risk Management

- Backend overload risk

- AI complexity

- Team dependency risks

Mitigation:

- Balanced workload

- Early development of complex modules

- Continuous coordination

# COST ESTIMATION

2.1 Overview

The cost estimation for the Online Quiz & Assessment System is developed using a structured and value-driven approach. The focus is not only on minimizing cost but on maximizing overall project value while accounting for uncertainty and risks.

The estimation considers:

- Project duration (3.5 weeks)

- Defined team structure (SPM1, SPM2, SPM3, SRE1, SRE2)

- Academic project constraints

- Use of free-tier tools and APIs

- Risk-adjusted budgeting approach

2.2 Cost Estimation Approach

A hybrid estimation strategy is used to ensure accuracy, validation, and risk handling:

- Bottom-Up Estimation → Detailed and most accurate

- Parametric Estimation → Mathematical validation

- Analogous Estimation → Early-stage approximation

- PERT Estimation → Handling uncertainty

- Risk-Based Contingency (EMV) → Financial risk adjustment

2.3 Cost Components Breakdown

The total project cost is divided into four major components:

- Direct Costs (Human Resources)

- Indirect Costs (Tools & Infrastructure)

- Contingency Reserve (Identified Risks)

- Management Reserve (Unidentified Risks)

2.4 Direct Cost Estimation (Bottom-Up Approach)

Formula:
Cost = Rate × Hours

| Resource | Rate (PKR/hour) | Hours | Cost (PKR) |
| --- | --- | --- | --- |
| SPM1 | 800 | 60 | 48,000 |
| SPM2 | 700 | 85 | 59,500 |
| SPM3 | 800 | 95 | 76,000 |
| SRE1 | 600 | 50 | 30,000 |
| SRE2 | 900 | 70 | 63,000 |

Total Direct Cost = PKR 276,500

This is based on detailed task-level estimation, making it the most reliable method.

2.5 Indirect Cost Estimation

| Item | Cost (PKR) |
| --- | --- |
| Cloud Hosting | 5,000 |
| AI API Usage | 10,000 |
| Internet & Utilities | 5,000 |
| Miscellaneous | 3,500 |

Total Indirect Cost = PKR 23,500

2.6 Contingency Reserve (Risk-Based)

Based on Expected Monetary Value (EMV) from risk analysis:

Contingency Reserve = PKR 35,000

Covers identified risks such as API overuse, delays, and technical uncertainties.

2.7 Management Reserve

Management Reserve is allocated for unforeseen risks:

Base Cost = 276,500 + 23,500 + 35,000 = 335,000

Management Reserve (5%) = PKR 16,750

Total Project Cost

Total Cost = Direct + Indirect + Contingency + Management Reserve

= 276,500 + 23,500 + 35,000 + 16,750
= PKR 351,750

2.8 Cost Estimation Techniques Applied

Analogous Estimation

- Based on similar academic systems

- Estimated range: PKR 300,000 – 380,000

Parametric Estimation

- Based on rate × hours

Average Rate ≈ 760 PKR/hour
Total Hours ≈ 360

Estimated Cost ≈ PKR 273,600

Confirms the reliability of bottom-up estimation.

Bottom-Up Estimation

- Resource-level detailed costing

- Final Direct Cost = PKR 276,500

PERT Estimation (Uncertainty Handling)

TE=(O+4M+P​)/6

(AI Module):
O = 15, M = 25, P = 45

Estimated Time ≈ 26.6 hours

Accounts for uncertainty in development tasks.

2.9 Budget at Completion (BAC)

A controlled budgeting approach is used:

- Direct Cost = 276,500

- Contingency Reserve (12%) = 33,180

Subtotal = 309,680

- Management Reserve (5%) = 15,484

BAC = PKR 325,164

This serves as the baseline for cost tracking.

2.10 Earned Value Management (EVM)

Key Metrics

- PV (Planned Value)

- EV (Earned Value)

- AC (Actual Cost)

Mid-Project Analysis

BAC = 325,164

- PV = 60% → 195,098

- EV = 50% → 162,582

- AC = 180,000

Performance Indicators

- CV = EV − AC = -17,418 → Over budget

- SV = EV − PV = -32,516 → Behind schedule

- CPI ≈ 0.90

- SPI ≈ 0.83

Forecasting

- EAC ≈ 361,293 PKR

- VAC ≈ -36,129 PKR

Control Threshold

- If CPI < 0.85 → Critical Condition

Corrective Actions

- Escalate to supervisor

- Apply scope reduction (MoSCoW)

- Control API usage

- Reallocate resources

2.11 Cost of Quality (CoQ)

Components

- Prevention Costs → Design, code reviews

- Appraisal Costs → Testing and validation

- Failure Costs → Bug fixing and rework

Boehm’s Rule

- Fix in design → 1× cost

- Fix in testing → 10× cost

- Fix after release → 100× cost

Early quality assurance significantly reduces overall cost.

Cost Control Strategy

The project ensures cost discipline through:

- Weekly cost monitoring

- API usage tracking

- Scope control using MoSCoW prioritization

- Resource reallocation (SPM ↔ SRE)

- Variance analysis (planned vs actual)

2.12 Return on Investment (ROI)

Investment

Total Cost (BAC) = PKR 325,164

Estimated Benefits

- Teacher Time Savings = 50,000

- Efficiency Gains = 30,000

- Reusability Value = 80,000

Total Benefits = PKR 160,000

Long-Term ROI

Total Benefits = 480,000

ROI ≈ 47.6%

Demonstrates long-term sustainability and value

Intangible Benefits

- Improved learning experience

- Instant feedback for students

- Reduced grading errors

- AI-based innovation

- High academic and scalability value