# RISK MANAGEMENT

## Risk Management Approach

The project will follow a PMBOK 8 uncertainty-based risk management approach, where both threats and opportunities are identified and managed to maximize project value.

- Risks will be identified using TECOP (Technical, External, Commercial, Organizational, Project Management) categories

- Risk analysis will include qualitative (Probability × Impact) and basic quantitative (EMV) techniques

- Each risk will have a defined owner and response strategy

- Risks will be continuously monitored throughout the project lifecycle

- A risk register will be maintained and updated regularly

## Risk Identification:

# R1 – Technical

- Because the AI model may not fully understand uploaded content, there is a risk that irrelevant or incorrect questions are generated, which could result in poor quiz quality and reduced user trust.

# R2 – Technical

- Because the system may face high concurrent usage, there is a risk that performance issues or system crashes occur, which could result in delays and failed quiz attempts.

# R3 – External

- Because the project depends on third-party AI APIs, there is a risk that API service becomes unavailable or changes, which could result in AI module failure.

# R4 – Organizational

- Because team members have limited experience with AI integration, there is a risk that development delays occur, which could result in missing deadlines.

# R5 – Project Management

- Because requirements may evolve during development, there is a risk that scope creep occurs, which could result in increased workload and timeline delays.

# OPP1 – Opportunity

- Because AI integration is innovative, there is an opportunity that the system gains high academic recognition, which could result in better grades and future project scalability.

## Risk Analysis

Qualitative Analysis (P × I)

| ID | Risk | P | I | Score | Priority |
| --- | --- | --- | --- | --- | --- |
| R1 | AI inaccurate output | 0.6 | 0.7 | 42 | Critical |
| R2 | System performance issues | 0.5 | 0.8 | 40 | Critical |
| R3 | API failure | 0.4 | 0.7 | 28 | High |
| R4 | Team skill gap | 0.5 | 0.6 | 30 | High |
| R5 | Scope creep | 0.6 | 0.5 | 30 | High |
| OPP1 | Academic recognition | 0.4 | 0.8 | 32 | Opportunity |

Quantitative Analysis (EMV)

| Risk | P | Impact (PKR) | EMV |
| --- | --- | --- | --- |
| R1 | 0.6 | -30,000 | -18,000 |
| R2 | 0.5 | -50,000 | -25,000 |
| R3 | 0.4 | -40,000 | -16,000 |
| OPP1 | 0.4 | +60,000 | +24,000 |

# Total EMV ≈ -35,000 PKR Recommended contingency reserve ≈ 35K PKR

## Risk Response Planning:

Threat Strategies (4Ts)

# R1 – AI Incorrect Questions → MITIGATE

- Add manual editing feature

- Test AI output before publishing

- Owner: AI Developer

- Trigger: >20% incorrect questions

# R2 – System Performance Issues → MITIGATE

- Optimize backend

- Use scalable services (Supabase)

- Owner: Backend Developer

- Trigger: Slow response > 3 sec

# R3 – API Failure → TRANSFER + MITIGATE

- Use backup API / fallback logic

- Cache generated questions

- Owner: Developer

- Trigger: API downtime

# R4 – Skill Gap → MITIGATE

- Use tutorials, documentation

- Divide tasks based on expertise

- Owner: Project Manager

# R5 – Scope Creep → AVOID

- Freeze requirements after approval

- Use MoSCoW prioritization

- Owner: Project Manager

Opportunity Strategy

# OPP1 – Academic Recognition → EXPLOIT

- Focus on AI feature quality

- Improve UI/UX for presentation

- Owner: Project Manager

## Contingency & Fallback Plans

Risk: AI generates poor questions

- Contingency Plan:

  - Allow teachers to edit questions

  - Use predefined question bank

- Fallback Plan:

  - Disable AI feature and use manual quiz creation only

## Risk Monitoring & Control

- Weekly risk review meetings

- Update risk register regularly

- Track risk status (Open / Closed / Mitigated)

- Identify new risks during development

- Reassess probability and impact

## Risk Register:

| ID | Risk | Cat. | P | I | Score | Owner | Strategy | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | AI inaccurate output | Tech | 0.6 | 0.7 | 42 | AI Dev | Mitigate | Open |
| R2 | Performance issues | Tech | 0.5 | 0.8 | 40 | Backend Dev | Mitigate | Open |
| R3 | API failure | External | 0.4 | 0.7 | 28 | Dev | Transfer | Open |
| R4 | Skill gap | Org | 0.5 | 0.6 | 30 | PM | Mitigate | Open |
| ID | Risk | Cat. | P | I | Score | Owner | Strategy | Status |
| R5 | Scope creep | PM | 0.6 | 0.5 | 30 | PM | Avoid | Open |
| OPP1 | Academic success | PM | 0.4 | 0.8 | 32 | Team | Exploit | Open |